## Sheet1
August 27th: Start our project , find and choose the idea suitable with the project
August 27th: We build up a plan what to do and divide tasks for members in our group
Application Parts | Coder | Actual Start Date | Doing Time
UI - Application layouts for whole parts | Ma Trung Kien | August 28th | 20 days
Employee - CRUD operations | Ma Trung Kien | August 28th | 12 hours
Book - CRUD operations | Nguyen Phuong Minh Thong | August 28th | 17 hours
Book - Issue Statement | Nguyen Phuong Minh Thong | Sept 10th | 10 hours
Book - Categories | Nguyen Phuong Minh Thong | Sept 20th | 2 days
Data Base | Nguyen Hong Son | August 28th | 1 week
Librarian - Log in Log out and Sign Up | Nguyen Hong Son | Sept 15th | 2 days
Book - Return Statement | Nguyen Hong Son | Sept 20th | 5 days
About | Nguyen Hong Son | Sept 25th | 30 minutes
FixBug | Nguyen Hong Son | Sept 25th | 3 days
Reporter : Nguyen Phuong Minh Thong